## EXERCISE 1
You are constructing 6 additional rooms on an office building. Each
of the six rooms is identical, and the projected cost for the project is
$100.000 and is expected to take 5 weeks.
At the end of the 2nd week, you have spent $17.500 per room and have
finished 2 rooms: you are ready to begin on the 3rd.
1. Based on the information provided in the example above, fill in the
values for the following table:
Value
Budgeted At Completion | $100.000
Planned Value | $40.000 | BAC x Planned%
Earned Value | $33.333 | BAC x Actual%
Actual Cost | $35.000
Cost Variance | $-1666,67 | EV-AC
Schedule Variance | $-6.666,67 | EV-PV
Cost Performance Index | 0.95 | EV/AC
Schedule Performance Index | 0.83 | EV/PV
Estimated At Completion | $105.263,15 | BAC/CPI
Estimated To Completion | $70.263,15 | EAC-AC
Variance At Completion | -5263 | BAC-EAC
To-Complete Performance Index | 1025 | (BAC-EV)/(BAC-AC)
2. Is the project ahead of or behind schedule?
Behind
3. Is the project going to be completed over or under budget?
Over Budget

## EXERCISE 2
You have planned for a project to write a software application to take I
year. The costs to this project are budgeted at $12.500 per month.
Six months into the project, you find that the software application is 50%
completed, and you have spent $70.000.
1. Based on the information provided in the example above, fill in the
values for the following table:
Value
Budgeted At Completion | $150.000
Planned Value | $75.000
Earned Value | $75.000
Actual Cost | $70.000
Cost Variance | $5.000
Schedule Variance | $0
Cost Performance Index | 1.07
Schedule Performance Index | 1
Estimated At Completion | 140.186
Estimated To Completion | 70.186
Variance At Completion | 9.814
To-Complete Performance Index | 0,9375
2. Is the project ahead of or behind schedule?
At Schedule
3. Is the project going to be completed over or under budget?
Under Budget

## .
Source:
THE PMP® EXAM - How to pass on your first try
Fourth Edition
Written by: Andy Crowe