## Risk Matrix
Breathe: Clear Guard | [10 empty] | Risk Reduction |  |  | Monitor & Control | [10 empty] | Damage | Probability | Effort
No. | Init Date | Risk | Probability | Damage | P | D | P*D | EW*S*P | SW relevant | SW-Klasse | Preventive action | Responsible | Date | Remaining Risk | Remain.P | Remain.D | E | P | D | Rem.P*D | A*EW*S | Responsible | SW-Klasse | Status | very low | very low | very low
1 |  | Environment: | [14 empty] | #REF! | 0 | 0 |  | #REF! |  |  |  | low | low | low
2 |  | High intensity natural disasters | very low | very high | 1 | 5 | 5 |  |  |  | acceptance |  |  | High intensity natural disasters | very low | very high | #REF! | 1 | 5 | 5 | #REF! |  |  |  | medium | medium | medium
3 |  | Low intensity natural disasters | low | high | 2 | 4 | 8 |  |  |  | transfer: Insurance company |  |  | Low intensity natural disasters | low | very low | #REF! | 2 | 1 | 2 | #REF! |  |  |  | high | high | high
4 |  | Pandemic shutdown | low | very high | 2 | 5 | 10 |  |  |  | acceptance |  |  | Pandemic shutdown | low | very high | #REF! | 2 | 5 | 10
5 |  |  |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF! |  |  |  | very high | very high | very high
6 |  | Project: |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF!
7 |  | Not enough funding is aquired | medium | medium | 3 | 3 | 9 |  |  |  | avoidance: Plan alternative funding methods |  |  | Cant find alternatives | very low | medium | #REF! | 1 | 3 | 3 | #REF!
8 |  | Project not approved by company | low | low | 2 | 2 | 4 |  |  |  | avoidance: Cooperate with company head early on |  |  | - |  |  | #REF! | 0 | 0 | 0 | #REF!
9 |  | Sick Workers delaying the project | medium | very low | 3 | 1 | 3 |  |  |  | mitigation: Have backup workers |  |  | Backup workers get sick | very low | very low | #REF! | 1 | 1 | 1 | #REF!
10 |  |  |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF!
11 |  | Technology: |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF!
12 |  | Research yields no success | low | very high | 2 | 5 | 10 |  |  |  | acceptance |  |  | Research yields no success | low | very high | #REF! | 2 | 5 | 10 | #REF!
13 |  | Research takes longer than expected | medium | high | 3 | 4 | 12 |  |  |  | mitigation: Hire more researchers / experts |  |  | Research takes longer than expected | very low | high | #REF! | 1 | 4 | 4 | #REF!
14 |  | Patent is released by other company | very low | low | 1 | 2 | 2 |  |  |  | acceptance: License the patent |  |  | - |  |  | #REF! | 0 | 0 | 0 | #REF!
15 |  |  |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF!
17 |  | Production: |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF!
18 |  | Pandemic (high demand phase) being over | medium | high | 3 | 4 | 12 |  |  |  | mitigation: Increased marketing efforts |  |  | Pandemic (high demand phase) being over | medium | low | #REF! | 3 | 2 | 6 | #REF!
19 |  | Material supply issues | low | medium | 2 | 3 | 6 |  |  |  | avoidance: Do contracts with different suppliers |  |  | - |  |  | #REF! | 0 | 0 | 0 | #REF!
20 |  | First batch does not satisfy requirements | low | high | 2 | 4 | 8 |  |  |  | mitigation: Apply improvements |  |  | After improvments still does not satisfy requirements | very low | high | #REF! | 1 | 4 | 4 | #REF!
21 |  |  |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF!
22 |  | Marketing: |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF!
23 |  | Competitor releases similar product | high | low | 4 | 2 | 8 |  |  |  | avoidance: Give a better offer |  |  | Competitor releases similar product | high | very low | #REF! | 4 | 1 | 4 | #REF!
24 |  |  |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF!
26 |  | Quality and Safety: |  |  | 0 | 0 | [10 empty] | #REF! | 0 | 0 |  | #REF!
27 |  | No health cerfitication | medium | very high | 3 | 5 | 15 |  |  |  | mitigation: Improve standards and re-apply for certification |  |  | No health cerfitication | very low | very high | #REF! | 1 | 5 | 5 | #REF!
28 |  | Product has quality issues and doesn't prevent infections | low | high | 2 | 4 | 8 |  |  |  | mitigation: Improve quality |  |  | Product has quality issues and doesn't prevent infections | very low | high | #REF! | 1 | 4 | 4 | #REF!